## Sheet1
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
|  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Player | 6 | 7 | bar: 3 to completed 9
Level 1-5 | 6 | 8 | bar: 3 to completed 9
Enemy 1 | 6 | 8 | bar: 3 to completed 6
Enemy 2 | 6 | 5 | bar: completed 9 to completed 12
Enemy 3 | 6 | 0 | bar: this week 15 to this week 18
UI | 3 | 2 | bar: 3
Menus | 6 | 7 | bar: 3 to completed 6
Testing | 9 | 6 | bar: 3 to completed 9
Boss | 11 | 0 | bar: 3 to completed 12
Pickups(barebones) | 6 | 9 | bar: 3 to completed 9
Unit_Testing | 3 | 9 | bar: completed 12 to this week 18
Pickup Effects | 9 | 3 | bar: this week 21
Player/enemy Sounds | 6 | 0 | bar: planned 24 to planned 27
Soundtrack | 18 | 0 | bar: planned 30 to planned 45
Player Statistics | 6 | 0 | bar: planned 48 to planned 51
group totals (hrs) | 107 | 64
group totals ($) | 11300 | 6400