## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Jeremy | 7200 | 6150 | 1050 | 4800 | 4500 | 300 | 1000 | 350 | 650 | 1400 | 1300 | 100
Parker | 8200 | 8350 | -150 | 6100 | 7000 | -900 | 1000 | 350 | 650 | 1100 | 1000 | 100
Total | 15400 | 14500 | 900 | 10900 | 11500 | -600 | 2000 | 700 | 1300 | 2500 | 2300 | 200

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
Parker |  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Player | 6 | 9 | bar: 3 to completed 9
Level 1-5 | 6 | 10 | bar: 3 to completed 12
Enemy 1 | 6 | 8 | bar: 3 to completed 6
Enemy 2 | 6 | 5 | bar: completed 9 to completed 12
Enemy 3 | 6 | 5 | bar: this week 15 to this week 18
UI | 3 | 4 | bar: 3 to completed 6
Testing | 9 | 6 | bar: 3 to completed 6
Menus | 8 | 9 | bar: 3 to completed 9
Boss | 11 | 14 | bar: 3 to this week 15
Total | 61 | 70
Jeremy
Pickups(barebones) | 6 | 9 | bar: 3 to completed 9
Unit_Testing | 3 | 9 | bar: completed 12 to this week 18
Pickup Effects | 9 | 12 | bar: this week 21 to planned 30
Player/enemy Sounds | 6 | 3
Soundtrack | 18 | 12 | bar: planned 24 to planned 45
Player Statistics | 6 | bar: planned 48 to planned 51
Total | 48 | 45
group totals (hrs) | 115 | 115
group totals ($) | 11500 | 11500

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Hours | 1.5 | 1 | 1
Parker | 3.5 | ü | ü | ü
Jeremy | 3.5 | ü | ü | ü
Total | 7 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Anne | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 7 | 5 | bar: 3 to 6
| Subtotal | 14 | 13
Bill | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Chris | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Dan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
| Total | 47 | 49
red is dependent on others